## Sheet1
TASK | ASSIGNED TO | PROGRESS | START | END
[5 empty] | Finished in time? |  | If no, then why?
design/tool review, pre implmentation | [5 empty] | date complete
Propose topic |  |  | 2020-09-01 | 2020-09-06 | YES | 2020-09-06
create use cases |  |  | 2020-09-28 | 2020-10-02 | YES | 2020-10-01
develop requirements |  |  | 2020-10-04 | 2020-10-07 | YES | 2020-10-06
Have GitHub set up |  |  | 2020-10-08 | 2020-10-08 | YES | 2020-10-08
SPMP completed |  |  | 2020-10-01 | 2020-10-21 | NO | 2020-11-04 | Had some questions about some parts and finished it a couple days after our design review meeting
Beginning of Implementation
purchas host (HostGator) |  |  | 2020-10-28 | 2020-10-28 | YES | 2020-10-28
purchase web domain(WordPress) |  |  | 2020-10-28 | 2020-10-28 | YES | 2020-10-28
develop a main menu and sections for the storage and products with HTML AND PHP |  |  | 2020-10-28 | 2020-11-02 | YES | 2020-11-02
create questionaire for application |  |  | 2020-09-28 | 2020-10-28 | YES | 2020-10-28
Task 5 |  |  | 2020-09-28 | 2020-10-01
Rest of Implementation + tests
Use PHP and JavaScript to develop the product and storage information |  |  | 2020-10-29 | 2020-11-07 | NO |  | Storage room is still not complete, idea was very challenging and may not be complete by the final due date but will try my best to do so and will have a plan to finish it even after.
Use CSS to clean up the site and make it visibly attractive |  |  | 2020-10-29 | 2020-11-14 | YES | 2020-11-12
create storage room using javascript |  |  | 2020-11-03 | 2020-11-10 | NO |  | storage room still not complete, struggling to create an actual visual room where you can make edits.
add section for maitenance |  |  | 2020-10-29 | 2020-11-02 | YES | 2020-10-30
Task 5 |  |  | 2020-11-03 | 2020-11-07
debugging and retests
test site and see any issues |  |  | 2020-11-10 | 2020-11-15 | YES | 2020-11-14
fix any issues |  |  | 2020-11-10 | 2020-11-15 | NO |  | Still some very minor issues with site and major issues with storage room so that is not fixed.
Task 3 |  |  | date | date
Task 4 |  |  | date | date
Task 5 |  |  | date | date
^^^^^ *This is the original plan*^^^^^
Formulas:
START = [END, row above]
START = [START, row above]
END = [START]+3